## Sheet1
The CS160 Squad's Gantt Chart (Trinh Nguyen, Anthony Trinh, Jervin Cruz) |  |  | 2016-08-29 | [6 empty] | 2016-09-05 | [6 empty] | 2016-09-12 | [6 empty] | 2016-09-19 | [6 empty] | 2016-09-26 | [6 empty] | 2016-10-03 | [6 empty] | 2016-10-10 | [6 empty] | 2016-10-17 | [6 empty] | 2016-10-24 | [6 empty] | 2016-10-31 | [6 empty] | 2016-11-07 | [6 empty] | 2016-11-14 | [6 empty] | 2016-11-21 | [6 empty] | 2016-11-28 | [6 empty] | 2016-12-05 | [6 empty] | 2016-12-12
Tasks | Time (Days) | Preds | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su
Start |  | Preds: --; 2016-08-29 T: Start
A. Come up with online/offline collaboration solutions | 3 | Preds: Start
B. Create Gantt Chart and Risk Management Chart | 5 | bar: Preds; 2016-08-29 Su to 2016-09-05 Th
C. Research Algorithm: Simple Sub Column Transposition (SSCT) | 18 | bar: Preds; 2016-09-12 M to 2016-09-26 M
D. Decide on potential programming language team will use | 2 | bar: Preds; 2016-09-26 T to 2016-09-26 W
E. Create a broad plan of how the team will implement a solution | 3 | bar: Preds; 2016-09-26 Th to 2016-09-26 Sa
F. Determine and assign tasks to each members | 2 | bar: Preds; 2016-09-26 Su to 2016-10-03 M
G. Design basic backend | 16 | bar: Preds; 2016-10-03 T to 2016-10-17 M
H. Add prototype UI frontend onto backend | 12 | bar: Preds; 2016-10-10 Sa to 2016-10-24 M
I. Testing the prototype | 2 | bar: Preds; 2016-10-17 Su to 2016-10-24 M
J. Present prototype to Client and obtain feedback | 1 | Preds: H, I
K. Continue working on prototype and make requested change | 15 | bar: Preds; 2016-10-24 W to 2016-11-07 M
L. Test the second prototype | 2 | bar: Preds; 2016-10-31 Su to 2016-11-07 M
M. Present second prototype to Client and obtain feedback | 1 | Preds: K, L
N. Add more features and improvements to the application | 26 | bar: Preds; 2016-11-07 W to 2016-11-21 T; 2016-11-28 M to 2016-12-05 M
O. Test the third prototype | 2 | bar: Preds; 2016-11-28 Su to 2016-12-05 M
P. Present third prototype to Client and obtain feedback | 1 | Preds: N, O
Q. Finalize and turn in project | 7 | bar: Preds; 2016-12-05 W to 2016-12-12 M
R. Biweekly 10-15 min status update meeting (Tuesday, Thursday) | bar: Preds; 2016-09-12 T; 2016-09-12 Th; 2016-09-19 T; 2016-09-19 Th; 2016-09-26 T; 2016-09-26 Th; 2016-10-03 T; 2016-10-03 Th; 2016-10-10 T; 2016-10-10 Th; 2016-10-17 T; 2016-10-17 Th; 2016-10-24 T; 2016-10-24 Th; 2016-10-31 T; 2016-10-31 Th; 2016-11-07 T; 2016-11-07 Th; 2016-11-14 T; 2016-11-14 Th; 2016-11-21 T; 2016-11-28 T; 2016-11-28 Th; 2016-12-05 T; 2016-12-05 Th